## Project Planner
AmaKaren Book App Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | WHO | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[7 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15
[7 empty] | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH
Create a database on Heidi | Amaka | 2 | 2 |  |  | 0%
Create a User Model | Karen | 4 | 2 |  |  | 0%
Create a Books to Lend Model | Karen | 4 | 2 |  |  | 0%
Create a Book review Model | Karen | 4 | 2 |  |  | 0%
Connect database | Amaka | 5 | 1 |  |  | 0%
Create a map box | Karen | 6 | 1 |  |  | 0%
Put user locations on the Map | Amaka | 7 | 1 |  |  | 0%
Implement cookies | Karen | 8 | 1 |  |  | 0%
Implement a Geolocation | Karen | 9 | 1 |  |  | 0%
Create a user login | Amaka | 10 | 2 |  |  | 0%
Implement a search box | Amaka | 10 | 2 |  |  | 0%
Create a user friendly UI | Karen | 12 | 4 |  |  | 0%
CSS Design | Karen | 12 | 4 |  |  | 0%
Implement the contact members | Amaka | 10 | 1 |  |  | 0%
Test application | AmaKaren | 16 | 2 |  |  | 0%